## GT V1 (2) (hidden)
South Wales Intermittent and Capital Maintenance Programme 2015/16
FRMS code (FR/**/S***) | FRMS name | Local Authority | Constituency | Catchment Flood Management Plan (CFMP) name | Shorline Management Plan (SMP) name | Job name | Description of work | NGR | Primary purpose | Secondary purpose | Asset type | Q1 work planned (%) | Q2 work planned (%) | Q3 work planned (%) | Q4 work planned (%)
FR19S002 | Cowbridge | Vale of Glamorgan | Vale of Glamorgan Co Const | Ogmore, Tawe (including Thaw and Cadoxton) |  | Cowbridge | Bank Repair / Access Improvement | SS 99770 74728 | Flood risk |  | Channel | 100%
FR19S002 | Cowbridge | Vale of Glamorgan | Vale of Glamorgan Co Const | Ogmore, Tawe (including Thaw and Cadoxton) |  | Cowbridge Reservoir | Access Track Repair | ST 00237 75203 | Flood risk |  | Channel |  | 100%
FR19S002 | Cowbridge | Vale of Glamorgan | Vale of Glamorgan Co Const | Ogmore, Tawe (including Thaw and Cadoxton) |  | Aberthin | Desilt & Channel Maintenance | ST827523 - ST021446 | Flood risk |  | Channel |  | 100%
FR19S002 | Cowbridge | Vale of Glamorgan | Vale of Glamorgan Co Const | Ogmore, Tawe (including Thaw and Cadoxton) |  | Llanblethian | Channel Maintenance | SS990741 - SS990740 | Flood risk |  | Channel |  | 100%
FR19S005 | Llancarfan - Upstream of Mill Race | Vale of Glamorgan | Vale of Glamorgan Co Const | Ogmore, Tawe (including Thaw and Cadoxton) |  | Llancarfan - Upstream of Mill Race | Desilt & Channel Maintenance | ST052706 - ST052702 | Flood risk |  | Channel |  |  | 100%
FR19S006 | Cadoxton | Vale of Glamorgan | Vale of Glamorgan Co Const | Ogmore, Tawe (including Thaw and Cadoxton) |  | Cadoxton Outfalls | Contingency Plan Improvements | ST1312167205 | H&S/Legal/Statutory |  | Structure | 100%
FR19S006 | Sully Moors Road | Vale of Glamorgan | Vale of Glamorgan Co Const | Ogmore, Tawe (including Thaw and Cadoxton) |  | Sully Moors Road | Desilt & Channel Maintenance | ST150686 - ST147685 | Flood risk |  | Channel |  |  | 100%
FR19S0019 | Grangetown | Cardiff | Cardiff | Taff and Ely |  | Grangetown | Wall repairs and Vegetation Clearance | ST1855274531 | Flood risk |  | Raised defence |  |  | 100%
FR19S019 | Grangetown | Cardiff | Cardiff | Taff and Ely |  | Cardiff Bay to Bridge | Tree Management | ST 17583 76782 To ST 17956 75778 | Flood risk |  | Raised defence |  |  | 100%
FR19S020 | Pontcanna | Cardiff | Cardiff | Taff and Ely |  | Gabalfa (Near Tesco) | Tree Management | ST 16182 78291 To ST 16682 78430 | Flood risk |  | Raised defence |  |  | 100%
FR19S022 | Amersham | Cardiff | Cardiff | Taff and Ely |  | Forest Farm Allotments | Tree Management | ST 13498 80760 To ST 13509 80545 | Flood risk |  | Raised defence |  |  | 100%
FR19S023 | Taffs Wells | Cardiff | Cardiff | Taff and Ely |  | Taffs Wells | Installation of Steps and Bank Clearance | ST 11826 83716 | Flood risk |  | Raised defence |  |  | 100%
FR19S023 | Taffs Wells | Cardiff | Cardiff | Taff and Ely |  | Taffs Wells | Asset Maintenance | ST118838 - ST121835 | Flood risk |  | Raised defence |  |  | 100%
FR19S025 | Hawthorn | Rhondda Cynon Taff | Rhondda Co Const | Eastern Valleys |  | Hawthorn | Blockstone Repair | ST 09252 87524 to ST 09572 87256 | Flood risk |  | Raised defence | 100%
FR19S028 | Taff Vale | Rhondda Cynon Taff | Rhondda Co Const | Eastern Valleys |  | Quakers Yard | AccessReinstatement | ST 09619 96551 | H&S/Legal/Statutory |  | Operation & Operability |  |  | 100%
FR19S035 | Robertstown | Rhondda Cynon Taff | Cynon Valley Co Const | Eastern Valleys |  | Robertstown | Shoal Removal | SO 00407 02966 | Flood risk |  | Channel |  |  |  | 100%
FR19S038 | Porth | Rhondda Cynon Taff | Rhondda Co Const | Eastern Valleys |  | Porth | Shoal Removal | ST 02443 91515 | Flood risk |  | Channel | 100%
FR19S041 | Mid Rhondda fawr | Rhondda Cynon Taff | Rhondda Co Const | Eastern Valleys |  | Treorchy | Removal of Old Structure | SS 95929 96699 | Flood risk |  | Structure | 100%
FR19S041 | Mid Rhondda fawr | Rhondda Cynon Taff | Rhondda Co Const | Eastern Valleys |  | Treherbert | Tree Management | SS 93952 98325 To SS 94152 98110 | Flood risk |  | Raised defence |  | 100%
FR19S041 | Mid Rhondda fawr | Rhondda Cynon Taff | Rhondda Co Const | Eastern Valleys |  | The Barracks - Ton Pentre | Shoal Removal | SS967959 - SS968957 | Flood risk |  | Channel | 100% |  | 100%
FR19S043 | Rhymney Cardiff | Cardiff | Cardiff | Taff and Ely |  | Llanrhymney | Tree Management & Acees Improvements | ST214074 to ST207795 | Flood risk |  | Raised defence |  | 50% |  | 50%
FR19S046 | Mid Rhymney, Pant Glas & Bedwas | Caerphilly | Caerphilly Co Const | Eastern Valleys |  | Bedwas House | Re profile embankment and Blockstone Repairs | ST160888 to ST162888 | Flood risk |  | Raised defence |  |  | 100%
FR19S049 | Nant Yr Aber | Caerphilly | Caerphilly Co Const | Eastern Valleys |  | Asda Caerphilly | Bank Re Profile and H&S improvements | ST 153880-153879 | Flood risk |  | Raised defence | 75% | 25%
FR19S054 | Brecon | Powys | Brecon and Radnorshire | Wye and Usk |  | Silver Street | Remove stockpiled Shoal for recycling | SO03897 - 28799 | Flood risk |  | Channel |  | 100%
FR19S056 | Caldicott Levels | Newport | Newport East Co Const | Wye and Usk |  | Monks Ditch | Removal of Sluice and adj. structures | ST 36912 82972 | H&S/Legal/Statutory |  | Structure |  | 100%
FR19S057 | Caldicott Levels | newport | Newport East Co Const | Wye and Usk |  | Mill Reen | Bank Repairs | ST 4357 8510 to ST 43717 85100 | Flood risk |  | Raised defence |  |  |  | 100%
FR19S067 | Ebbw Bridge, Tredegar Park | Newport | Newport East Co Const | Eastern Valleys |  | Ebbw Bridge, Tredegar Park | Shoal Removal | ST2938986016 | Flood risk |  | Raised defence |  |  | 100%
FR19S067 | Ebbw Bridge, Tredegar Park | Newport | Newport East Co Const | Eastern Valleys |  | St Brides Gardens | Access ramp Improvements | ST 29489 85955 | Flood risk |  | Raised defence | 100%
FR19S077 | Llantarnam | Powys | Brecon and Radnorshire | Wye and Usk |  | Llantarnam Way | Tree Management | ST29488 - 93728 | Flood risk |  | Channel |  |  | 100%
FR19S081 | Monmouth | Monmouthshire | Brecon and Radnorshire | Wye and Usk |  | Monmouth | Embankment and other Structural Repairs | SO 50438 12641
FR19S090 | Ebbw FAS 1 | Caerphilly | Caerphilly Co Const | Eastern Valleys |  | Risca/ Rear of Braithwaites | Blockstone Repair | ST244897 to ST245895 | Flood risk |  | Raised defence |  | 100%
FR19S090 | Pontimister | Caerphilly | Caerphilly Co Const | Eastern Valleys |  | Pontimister | Blockstone Repair | ST249896 | Flood risk |  | Raised defence |  | 100%
FR19S094 | Caldicott Levels | Newport | Newport East Co Const | Wye and Usk | Anchor Head to Lavernock Point | Caldicot Levels | Access improvements | Various | H&S/Legal/Statutory |  | Operation & Operability |  | 100%
FR19S095 | Caldicott Levels | Newport | Newport East Co Const | Wye and Usk | Anchor Head to Lavernock Point | Mathern Rise | Bush Clearance / New Fencing | ST53668 -90928 to 52303 -89864 | H&S/Legal/Statutory | Flood risk | Channel |  | 100%
FR19S095 | Caldicott Levels | Newport | Newport East Co Const | Wye and Usk | Anchor Head to Lavernock Point | Mathern Outfall | Desilt in front of Outfall | ST 52936 - 90161 | Flood risk | H&S/Legal/Statutory | Channel |  | 100%
FR19S102 | Upstream of Abergavenny | Monmouthshire | Monmouth | Wye and Usk |  | Llanwenarth Ditch | Desilt | SO27199-15224 to SO28106-14555 | Flood risk |  | Channel |  |  | 100%
FR19S102 | Upstream of Abergavenny | Monmouthshire | Monmouth | Wye and Usk |  | Nantiago | Desilt | SO28018-15085 to SO28429 - 14431 | Flood risk |  | Channel |  |  | 100%
FR19S106 | Upstream of Brecon | Powys | Brecon and Radnorshire | Wye and Usk |  | Lower Chapel Bridge | Shoal management around road bridge | SO02937-35538 | Flood risk |  | Raised defence |  | 100%
FR19S134 | Usk Town | Powys | Brecon and Radnorshire | Wye and Usk |  | Usk Town | Remove silt island | SO 37429 - 00570 | Flood risk |  | Channel |  | 100%
FR19S135 | Rhosog Fach | Cardiff | Cardiff South and Penarth Boro Const | Eastern Valleys | Anchor Head to Lavernock Point | Rhosog Fach | Sea Door replacement and Improvement Works | ST 23300 77698 | H&S/Legal/Statutory |  | Structure |  | 100%
Note on A1: Kelland, Richard:

## South Wales 2019_20
South Wales Intermittent and Capital Maintenance Programme 2019/20
FRMS code (FR/**/S***) | FRMS name | Local Authority | Catchment Flood Management Plan (CFMP) name | Shorline Management Plan(SMP) name | Job name | Description of work | NGR | Primary purpose | Secondary purpose | Asset type | Q1 work planned (%) | Q2 work planned (%) | Q3 work planned (%) | Q4 work planned (%)
FR/19/S005 | Llancarfan - Upstream of Mill Race | Vale of Glamorgan | Ogmore, Tawe (including Thaw and Cadoxton) |  | Llancarfan - upstream of Mill Race | Desilt and channel maintenance | ST052706 - ST052702 | Flood risk |  | Channel |  |  | 100%
FR/19/S006 | Cadoxton | Vale of Glamorgan | Ogmore, Tawe (including Thaw and Cadoxton) |  | Wimbourne Road | Weed cut | ST150686 - ST147685 | H&S/Legal/Statutory |  | Structure |  |  | 100%
FR/19/S007 | Sully Moors Road | Vale of Glamorgan | Ogmore, Tawe (including Thaw and Cadoxton) |  | Sully Moors Road | Desilt and channel maintenance | ST150686 - ST147685 | Flood risk |  | Channel |  |  | 100%
FR/19/S015 | Tonyrefail | Rhondda Cynon Taff | Eastern Valleys |  | Pontyclun | Blockstone repairs | ST0391384703 | Flood risk |  | Raised defence |  | 100%
FR/19/S019 | Grangetown | Cardiff | Taff and Ely |  | Sophia Gdns | Tree management | ST1705578062 to ST1754676893 | Flood risk |  | Raised defence |  |  |  | 100%
FR19S022 | Amersham | Cardiff | Taff and Ely |  | Mellingriffith | Bank repair | ST1354280502 | Flood risk |  | Raised defence |  |  |  | 100%
FR/19/S023 | Taffs Wells | Cardiff | Taff and Ely |  | Nantgarw | Tree management | ST1127185580 to ST1167785477 | Flood risk |  | Raised defence |  |  | 100%
FR/19/S023 | Taffs Wells | Cardiff | Taff and Ely |  | Taffs Wells | Asset maintenance | ST118838 - ST121835 | Flood risk |  | Raised defence |  |  | 100%
FR/19/S026 | Webbs bridge | Rhondda Cynon Taff | Eastern Valleys |  | Treforest | Revetment scour repairs | ST1626087553 - ST1609587361 | Flood risk |  | Raised defence | 100%
FR/19/S026 | Webbs bridge | Rhondda Cynon Taff | Eastern Valleys |  | Treforest | Deshoal | ST1075286687 | Flood risk |  | Raised defence |  | 100%
FR/19/S028 | Taff Vale | Rhondda Cynon Taff | Eastern Valleys |  | Aberfan | Shoal removal | ST1075286687 | Flood risk |  | Channel |  |  | 100%
FR/19/S028 | Taff Vale | Rhondda Cynon Taff | Eastern Valleys |  | Aberfan | Tree management | SO0737500429 to ST0753099628 | Flood risk |  | Channel |  |  |  | 100%
FR/19/S033 | Mountain Ash | Rhondda Cynon Taff | Eastern Valleys |  | Mountain Ash | Shoal removal | ST0476899193 | Flood risk |  | Channel |  | 100%
FR/19/S038 | Porth | Rhondda Cynon Taff | Eastern Valleys |  | Porth | Shoal removal | ST0244191564 | Flood risk |  | Channel | 100%
FR/19/S041 | Mid Rhondda fawr | Rhondda Cynon Taff | Eastern Valleys |  | Pontyclun | Shoal removal | ST0348481513 | Flood risk |  | Channel | 100%
FR/19/S041 | Mid Rhondda fawr | Rhondda Cynon Taff | Eastern Valleys |  | Gelli | Shoal removal | SS9774294980 | Flood risk |  | Channel |  |  | 100%
FR/19/S041 | Mid Rhondda fawr | Rhondda Cynon Taff | Eastern Valleys |  | The Barracks - Ton Pentre | Shoal removal | SS967959 - SS968957 | Flood risk |  | Channel | 100% |  | 100%
FR/19/S046 | Mid Rhymney, Pant Glas & Bedwas | Caerphilly | Eastern Valleys |  | Bedwas House | Regrade and reseed of eroded bank | ST1599788852-ST1592788889 | Flood risk |  | Raised defence |  | 100%
FR/19/S046 | Mid Rhymney, Pant Glas & Bedwas | Caerphilly | Eastern Valleys |  | Nant Y Bwch | Regrade and reseed of eroded bank | ST1650288405-ST1668788383 | Flood risk |  | Raised defence |  | 100%
FR/19/S047 | Ystrad Mynach & Llanbradach | Caerphilly | Eastern Valleys |  | Ystrad Mynach | Shoal removal | ST1462293017 - ST1461392967 | Flood risk |  | Raised defence |  | 100%
FR/19/S049 | Nant Yr Aber | Caerphilly | Eastern Valleys |  | Pontygwindy | Scour repairs | ST1565288364 | Flood risk |  | Raised defence |  | 100%
FR/19/S050 | Porset Brook | Caerphilly | Eastern Valleys |  | Lansbury Park | Revetment scour repairs | ST1565288364 | Flood risk |  | Raised defence | 50% | 50%
FR/19/S056 | Caldicott Levels | Newport | Wye and Usk |  | Monks Ditch | Tidal outfall repairs | ST3691282972 | Flood risk |  | Structure |  | 100%
FR/19/S057 | Caldicott Levels | newport | Wye and Usk |  | Windmill Reen | Tidal outfall repairs | ST4097983165 | Flood risk |  | Structure |  | 100% |  | 100%
FR/19/S076 | Llanhilleth and Aberbeeg | Blaenau Gwent | Eastern Valleys |  |  | Blockstone reprofile | SO 20974 01790 to SO 20964 01760 | Flood risk |  | Raised defence | 50% | 50%
FR/19/S087 | Ponthir | Torfaen | Wye and Usk |  | Ponthir embankment | Embankment reprofile | ST39203320 | Flood risk |  | Raised defence |  | 50% | 50%
FR/19/S090 | Ebbw FAS 1 | Caerphilly | Eastern Valleys |  | Risca - Dan Y Graig | Access improvements | ST2361790559 | H&S/Legal/Statutory |  | Raised defence | 25% | 75%
FR/19/S090 | Ebbw FAS 1 | Caerphilly | Eastern Valleys |  | Risca - Gladstone Street | Access improvements | ST2361790559 | H&S/Legal/Statutory |  | Raised defence |  | 100%
FR/19/S111 | Upstream of Crosskeys | Newport | Eastern Valleys |  | Cross Keys | Access improvements | ST 2194391368 | H&S/Legal/Statutory |  | Raised defence | 100%
FR/19/S134 | Usk Town | Powys | Wye and Usk |  | Usk Town | Remove silt island | SO3742900570 | Flood risk |  | Channel |  | 100%
FR/19/S135 | Wentlooge Levels 1 | Cardiff | Wye and Usk | Anchor Head to Lavernock Point | Rhosog Fach | Culvert replacement and improvement works | ST2330077698 | H&S/Legal/Statutory |  | Structure |  | 100%
FR/19/S135 | Wentlooge Levels 1 | Cardiff | Wye and Usk | Anchor Head to Lavernock Point | Peterstone Gout | Bank re-instatement - improvement works | ST2767680524 | H&S/Legal/Statutory |  | Structure |  | 100%
FR/19/S137 | Ynysddu | Caerphilly | Eastern Valleys |  | Ynysddu | Blockstone repairs | ST1793592508 | Flood risk |  | Raised defence |  |  | 100%
FR/19/S150 | Llanelli | Carmarthenshire | Loughor to Taf | Lavernock Point to St Ann's Head | Dafen at Trostre | Bank repairs | SS5189599174 & SS5220299127 | Flood risk |  | Raised defence |  | 50% | 50%
FR/19/S150 | Llanelli | Carmarthenshire | Loughor to Taf | Lavernock Point to St Ann's Head | Trostre berm improvements | Access improvements to the river bank | SS5249699515 | Flood risk | H&S/Legal/Statutory | Channel | 25% | 50% | 25%
FR/19/S153 | Morlais at Crofty | Swansea | Loughor to Taf | Lavernock Point to St Ann's Head | Crofty access and storage | Access gate to field and storage box for stoplogs and sandbags | SS5269994788 | H&S/Legal/Statutory | Flood risk | Raised defence |  |  | 75% | 25%
FR/19/S156 | Tawe | Swansea | Ogmore, Tawe (including Thaw and Cadoxton) | Lavernock Point to St Ann's Head | Ynystawe Park | Floodbank repairs | SS6842799960 | Flood risk | H&S/Legal/Statutory | Raised defence |  | 50% | 50%
FR/19/S164 | Neath | Neath Port Talbot | Ogmore, Tawe (including Thaw and Cadoxton) | Lavernock Point to St Ann's Head | Glynneath expansion joints | Replacing the expansion joint materials | SN9733705859 | Flood risk |  | Raised defence |  | 50% | 50%
FR/19/S167 | Afan | Neath Port Talbot | Ogmore, Tawe (including Thaw and Cadoxton) | Lavernock Point to St Ann's Head | Afan at Port Talbot | Gravel removal and vegetation management | SS7662790250 | Flood risk |  | Channel | 75% | 25%
FR/19/S197 | Tenby | Pembrokeshire | Pembrokeshire and Ceredigion Rivers | Lavernock Point to St Ann's Head | Tenby buoy | Replace with piled mark | SS1329099812 | H&S/Legal/Statutory |  | Structure | 25% | 50% | 25%
FR/19/S201 | Pendine | Pembrokeshire | Pembrokeshire and Ceredigion Rivers | Lavernock Point to St Ann's Head | Salthouse and Railsgate Pil floodbank | Repairs to eroded areas | SN3039009729 | Flood risk |  | Raised defence |  |  | 50% | 50%
FR/19/S218 | Johnstown | Carmarthenshire | Loughor to Taf | Lavernock Point to St Ann's Head | Tawelan Brook Pembrokeshire Hedge Bank | Repairs to improve the defence | SN3979019644 | Flood risk |  | Raised defence |  |  | 50% | 50%
FR/19/S247 | Llanbadarn | Aberystwyth | Loughor to Taf | St Ann's Head to Gread Ormes Head | Glan-yr-afon | Sheet piling repair | SN6072680292 | Flood risk |  | Raised defence |  |  | 50% | 50%
FR/19/S262 | Dulais at Pwll | Carmarthenshire | Loughor to Taf | Lavernock Point to St Ann's Head | Pwll | Vegetation management and construct flood bund | SN4862900762 | Flood risk |  | Raised defence | 75% | 25%
FR/19/S308 | Confluence Area | Powys | Wye and Usk |  | Criggion embankment | Embankment repairs | ST39203320 | Flood risk |  | Raised defence |  | 100%
Note on A1: Kelland, Richard: